## Sheet1
16 weeks til end of June
200 hours max in project
12.5 hours per week -- set project work hours - will spread over 2 days of the week
Any weeks I go under that number the hours missed will be recorded in this plan and added on to future work weeks
Week | Week end date | Tasks | Description | Obstacles | Milestones
Week 1 | 2024-03-17 | Setup/research | Make a project plan, log on to server, download libraries, start lit review
Week 2 | 2024-03-24 | Research/finish setup | Literature review to find start point, iron out any setup issues |  | Run Pistonball example
Week 3 | 2024-03-31 | Find best solution to problem | Finish Bulk of Lit Review, use it to finalise approach | Making good starts on coursework// big group project proposal due | Formulate simple env
Week 4 | 2024-04-07 | Simulation implementation | initialise sim environment | Lots of coursework progress needed | Experiment with example//try on server
Week 5 | 2024-04-14 | Implement simulation | Finalise simulation environment | Lots of coursework progress needed
Week 6 | 2024-04-21 | Optimise sim | Evaluate and possible optimisation of sim |  | Own environment implemented
Week 7 | 2024-04-28 | Initialise MARL algorithm | Implement petting zoo environment and build algorithm | 1 coursework due this week
Week 8 | 2024-05-05 | Finalise MARL algorithm | Finalise MARL algorithm/optimise | 1 coursework due this week
Week 9 | 2024-05-12 | Run both together | Initialise sim communication with MARL algorithm implementation | 1 coursework due this week
Week 10 | 2024-05-19 | Working sim | Finalise working sim/optimise | 1 coursework due this week
Week 11 | 2024-05-26 | Optimisation | Optimisation of running sim | 1 coursework due this week
Week 12 | 2024-06-02 | Optimisation | Optimisation of running sim
Week 13 | 2024-06-09 | Final output | Final optimisation / produce output of running sim with algorithm
Week 14 | 2024-06-16 | Report findings | Write report on findings | Very busy week of booked plans
Week 15 | 2024-06-23 | Report writing | Write report on findings
Week 16 | 2024-06-30 | Finish report | Write report on findings
I've given myself extra weeks than necessary in places such as report writing and possibly optimisation as obstacles may prove to get in the way//I may struggle more than anticipated
I also have 4 weeks beyond this plan as breathing space if the hours arent finished and will use this to reach an end I am happy with.
Obstacles have been stated, however, if I stick to my set hours provided, due to them being evenly spread and also my coursework deadlines are evenly spread, I should be able to make progress...
Consistently despite obstacles. Biggest realistic possible obstacle is taking wrong approaches, or an unrealistic plan, so this may be subject to change.